## ASSIGNMENTS
ASSIGNMENTS |  |  |  | Priority 1:
Priority 2:
|  |  |  | Priority 3: |  |  | 0
Ref # / Link | TAB (Category) | WHO | WHAT | Description |  | Completion Date | Comments
| COLLATERAL | Amanda | Booth | needed for 2020 | 1 | 2015-10-05 | Amanda was going to put in order 10/2/15. Furniture and electrical are ordered.
| COLLATERAL | Ariena | Promos/Swag/Tshirts | Needed for 2020, t-shirts need to be ordered by Oct 5 | 1 | 2015-10-06 | T-shirts ordered, expected arrival Oct 20
|  | Ariena | Order Business Cards | Needed for 2020; Design work by first week of Oct; Ordering printing is quick | 1 | 2015-10-09 | Ordered, Delivery is Oct 16
Physical Presence
Logo
Sign for front desk
Signage on doors
Building Sign
| FRONT END | Caton | Legal Messaging | review legal terms on website. Includes T&C's, Privacy, & FCRA Acknowledgement | 1 | 2015-10-01 | T&C's & Privacy complete. Waiting on Ben to update sign up process with FCRA Acknowledgement.
| FRONT END | Caton | Alert Messages | ensure language specific to creditera is changed to Nav | 1 | 2015-10-07 | Spoke with QA team. They anticipate a trickle of additional items that will have to be changed as we see them moving forward, especially with error messages and alerts because there is no way to test them until they happen in real life.
| FRONT END | Caton | Copy - changing Creditera to nav across entire product | need to go through website page by page to change info | 1 | 2015-10-07 | Same as above
| BACK END | Caton | Recurly | SAM: Will call RECURLY to help with testing. | 2 | 2015-10-20 | Need to change our vanity URL to nav at go live date. To do this, we must contact Recurly. Additionall, we'll need to change the company details with Recurly.***NOT CHANGING VANITY URL UNTIL AFTER*** | mobile and web endpoints need to be reviewed. Look for vanity URL
| BACK END | Caton | Switch Recurly email templates | Needs to happen on go live date. | 2 | 2015-10-20 | Simply requires copying and pasting new HTML code into Recurly email templates. Dede is working on templates.
| BACK END | Caton | Help Text |  |  |  | duplicate subpart of line 15
| WEBSITE | Caton | Knowledge & Help Sections |  |  |  | duplicate subpart of line 15
| WEBSITE | Caton | Coupon | shouldn't be an issue
Business cards
Posters
Vehicle parking ID / wraps
Building ID badges
Letterhead
Envelopes
T-shirts/uniforms
Swag/promotional items
Brochures
Slide decks/presentations
Voicemail message
Online Presence
also see Social Media tab
Domain name
SSL certificate
| SOCIAL MEDIA | Greg | KSL News/AP News - Press Release |  | 2 | 2015-10-21 | Marketing (Jared)
| SOCIAL MEDIA | Caton | Trademarks | Nav trademark has been filed. | 1 | 2015-07-01
Web pages
Website copyright
Search engines
Email addresses
Email signatures
Wikipedia page
Social Media
Facebook page
Twitter
LinkedIn
Wikipedia
YouTube
Pinterest
Instagram
| BACK END | Dave | Product demo | Product demo for use at 2020 and with key influencers | 2 | 2015-10-20 | approved by Jesse
| COLLATERAL | Caton | New T-shirts |  | 1 | 2015-10-05
| COLLATERAL | Caton | Stickers/Decals |  | 1 | 2015-10-06
Legal
Business License
Contracts
| CONTRACTS | Caton | Authorize. net | Ready to go with Authorize. Just need to tell them the new name when we are ready to go live with the change. | 2 | 2015-10-20
Patents
Trademarks
Copyrights
Department of Corporations or state agency registration
| CONTRACTS | Caton | NewTek Merchant Processor | email sent to T. Harkins at Newtek to get info. | 2 | 2015-10-20 | Ready to go--Automatic Update evening of Oct 20, which will be ready and live the next day on the 21st.
Stock certificates
Notify registered agent
Financial
Bank Accounts
Checks
Business Credit Agencies
Credit Cards
Contracts with Lenders/Vendors
HR
Payroll
| OTHER | Caton | Stickers | need to design |  |  | Duplicate
| WEBSITE | Caton | Recurly email notifications |  | 1 | 2015-10-06 | Need to make a new task for email switchover when we go live.
Health insurance
| FRONT END | DAVE | Engineering Product Review Tab | See 1.1 ENGINEERING PRODUCT REVIEW TAB | 1 | 2015-10-06 | #REF!
Other insurance (dental, life, etc.)
| BACK END | Dave | Webhooks | Webhooks are IP address specific. Only needs to be looked at if they are domain name related. Hang | 1 | 2015-10-01 | Main IP is not changing
Unemployment insurance
| BACK END | Dave | Twilio | Look into changes associated with simple name change. Dave | 1 | 2015-10-01
| BACK END | Dave | Mandrill | Look into changes associated with simple name change. Dave | 1 | 2015-10-01 | The domain needs to be changed in the allosaurus environments files once it has been added on Mandrill's dashboard.
| BACK END | Dave | Member Admin | No change expected | 2 | 2015-10-13
| BACK END | Dave | Database | No change expected | 2 | 2015-10-13
| BACK END | Dave | File/class names (code) Class namespacing | Refactor across everything. Search and replace function. Shouldn't be too challenging. Need to create a Nav branch off of production to be deployed for rebrand. |  | n/a | will be done when rewriting java code. Don't change this stuff now.
| BACK END | Dave | Push Notifications | No change expected | 1 | 2015-10-01 | What is this for?
| WEBSITE | Dave | Database | No change expected |  | n/a | no change
401K
Job boards
| SOCIAL MEDIA | Dave | Fundastic | Still need to ingest. Nothing really changes. Greg has placed this as a high priority | 1 | 2015-10-12 | Try to leave fundastic up until fully ingested. Then take down--fundastic redirect to nav.com Tim D is leading this effort. The posts are migrated and about done with calculators. We will save a complete copy of that site so we can move more of the content over post rebrand. Tim is still working on the redirect map and has a few more pages that get a decent amount of traffic to port over, but he's done.
Employee shares
Training manual
| CONTRACTS | Dave | Precise ID | No change expected | 1 | 2015-10-01 | Dave: email each bureau and ask
| CONTRACTS | Dave | Mailchimp | Look into changes associated with simple name change. Dave | 1 | 2015-10-01
Telephone scripts
| CONTRACTS | Dave | WebFaction | Look into changes associated with simple name change. Dave | 1 | 2015-10-12 | They can't rename the account. This is not public facing and doesn't need to be switched over.
| ACCOUNTS | Dave | Bureaus in General (XPN, TU & D&B) | Dave is currently working on this. | 1 | 2015-10-12 | Conversing with technical folks at the bureaus. This is a duplicate task. Both Caton and Dave have it listed on their respective lists. Caton has completed the task.
| ACCOUNTS | Dave | Screen caps for TU | Dave is currently working on this. | 1 | 2015-10-06 | Completed by Caton
| ACCOUNTS | Dave | Bugsnag | Look into changes associated with simple name change. Dave | 1 | 2015-10-01 | Investigate
| ACCOUNTS | Dave | New Relic | Look into changes associated with simple name change. Dave | 1 | 2015-10-01 | Investigate
| Other | Dave | Haroku Acccount and AWS Account for Fundastic | Domain Ownership | 1 | 2015-10-12 | Try to leave fundastic up until fully ingested. Then take down--fundastic redirect to nav.com Hang is working with Mike and Tim D.
| BACK END | Dave/Hang | Env., Stub Prod, Integration | This is all Hang. Currently in progress | 1 | 2015-09-30
| FRONT END | Dave | Default Affiliate | needs to be done in allosaurus | 2 | 2015-10-20 | when we create a member, need nav listed as affiliate (change name of affiliate)
| FRONT END | Dede | Downloadable Content: Videos (listed separately), Help Text, Contact Info/wording, PDF Footer |  | 1 | 2015-10-01
| WEBSITE | Dede | Affiliate/Partner Pages | Part of Web Plan | 1 | 2015-09-30
| WEBSITE | Dede | Team Page | almost | 2 | 2015-09-30
| WEBSITE | Dede | Pricing Page | Part of Web Plan | 1 | 2015-09-30
| WEBSITE | Dede | Banner Ads | Design work | 1 | 2015-10-05 | questions? Talk to Joel
| WEBSITE | Dede | Affiliate Ads | Design work | 1 | 2015-10-05 | questions? Talk to Joel
| WEBSITE | Dede | Blur Creditera swag in pictures | n/a - not necessary
Media/Advertising
| COLLATERAL | Dede | Business Cards | design done; not printed | 1 | 2015-10-12 | Assigned to Krissie
| COLLATERAL | Dede | Posters | printed in time for Money 2020 | 1 | 2015-10-12
|  | Dede | Booth Design | work with Amanda | 1 | 2015-10-12
| COLLATERAL | Dede | Handouts (SBDC) | included in the collateral plan | 1 | 2015-10-07
| COLLATERAL | Dede | Envelopes | included in the collateral plan | 1 | 2015-09-30
| COLLATERAL | Dede | Letterhead | included in the collateral plan | 1 | 2015-09-30
| COLLATERAL | Dede | Slide deck template | included in the collateral plan | 1 | 2015-10-08
| COLLATERAL | Dede | Pass along cards | included in the collateral plan | 1 | 2015-10-07
| COLLATERAL | Dede | Email Templates | Almost ready, not including Recurly emails (through CS) | 1 | 2015-09-30
| WEBSITE | Dede | Emails, Recurly, Marketo | marketing emails are Dede | 1 | 2015-10-06
| WEBSITE | Calvin/Dede | Videos | Part of downloadable content | 1 | 2015-10-13 | Videos are done but need some copy changes
| FRONT END | Design team | Branding (logo) & Colors | COMPLETE | 1 | 2015-09-15
| SOCIAL MEDIA | Tim G | Key influencer | message to SBA, others | 1 | 2015-10-13 | Working with Hatim to coordinate this. On schedule for Oct 10 release
| SOCIAL MEDIA | Greg | Partners Pre Commuication and Launch Announcement | 2015-10-10 | 1 | 2015-10-13 | On track for Oct 10 release. Hang will be included on the contact list when the Affiliate text is ready.
Press release
Online press resources
Media style guide
Online advertisements
Billboards/Outdoor ads
Radio ads
TV ads
| FRONT END | Hang | Redirect URLs for members | Need to map the timeline and changes | 2 | 2015-10-20 | Keeping members.creditera. Mike is doing a redirect for bookmarked members
| FRONT END | Hang | App.Nav.Com or my.nav.com | Need to decide (Marketing/Exec needs to decide) | 1 | 2015-09-24 | app.nav.com
| BACK END | Hang | email list | hang has been testing with UIUX | 2 | 2015-10-14 | Spreadsheet is coming with instructions (Hang)
| BACK END | Hang | Auto Responders | if people are still emailing a creditera email they need a notification to use nav email | 2 | 2015-10-14 | Spreadsheet is coming with instructions (Hang)
| WEBSITE | Hang | SSL Certs | Should be completed by end of week 9/25 | 1 | 2015-10-06 | almost done; some done after; submitted, waiting to be issued
| WEBSITE | Hang | Redirect from old URLS to new | need to map the timeline and changes | 2 | 2015-10-20 | day of flip
| WEBSITE | Hang | DNS | Is ready to go when necessary | 2 | 2015-10-20 | close to done
| SOCIAL MEDIA | Hang/Dede | Email Signatures | Just need to verify. Send a couple people can use with new brand | 2 | 2015-10-20 | Amanda sent Dede's approved options for signatures
Third Party Tools
| CONTRACTS | Hang | Google Apps | switchover to Nav (duplicate) | 1 | 2015-10-10 | aliases are P1 but the account switchover is P3
| OTHER | Hang | IP Block Removal on app.nav.com and nav.com (Oct 16) | IP Block Removal on app.nav.com and nav.com (Oct 16) | 2 | 2015-10-16 13:00
Office email
Email marketing program
Phone conferencing service
Online conferencing service
Office software platform
Shared folders
| WEBSITE | Hang | spf for nav | spf entries for email marketing | 1 | 2015-10-01
Google Maps listing
| BACK END | QA & Hang | Potential of things breaking when other things go offline | mostly just a catch all | 2 | 2015-10-20
| SOCIAL MEDIA | Hatim/Hang | Backlink Redirects | Reassign assets with AirFoil (Sean); New Social channels, requires pre communication and then in the moment communcation | 1 | 2015-10-16 | Hang is working with Tim.
| WEBSITE | Hatim | URL Mapping | Map content we have on Creditera and Fundastic over to NAV (Content and URLs) Redirects | 1 | 2015-10-16
Inter office messaging program
| Other | Hatim | Migrate Fundastic Content to NAV |  | 1 | 2015-10-16 | 2015-10-08
| Other | Hatim | Transfer Ownership of Fundastic to Nav (at Go Daddy leve) | Requires Hang | 1 | 2015-10-16
| Other | Hatim | Make a backup copy of Creditera and Fundastic | Hatim will work with Binary M who's helping with Migration. Then our Dev team can grab it from there. | 1 | 2015-10-16
| OTHER | Hatim | Site Migrations | Switch search console to let them know C = Nav, same for Fundastic --> Nav (Site address change) | 2 | 2015-10-20
| WEBSITE | Jared | Company Page | Due Oct 6th | 1 | 2015-10-05 | https://docs.google.com/document/d/1psO4InT2Aa_VkD-HdZOlUDPqkNTBqGbcoXQRjwoLkPM/edit
| WEBSITE | Jared | Blog Post explaining the transition on the home page | Announcement | 1 | 2015-10-02 | https://docs.google.com/document/d/1cV2_NS5thuz54S0cN1KEES7pgifAzL2gWlultLZi9bE/edit
| SOCIAL MEDIA | Jared | PR plan and release final |  | 1 | 2015-10-12 | Complete pending final Greg approval
| CONTRACTS | Jared | Member Communication/Founders Letter | Logan, prior to Oct 10 | 1 | 2015-10-16 | Complete by 10/14. Pivoted, now a Letter from Levi https://docs.google.com/spreadsheets/d/1xj-EvTmUiJSVRZJHqnXO95Q8be6pVv5g206Z1wCX9CU/edit#gid=0
| CONTRACTS | Jared | Partner, Affiliate Communication | Prior to Oct 10 | 1 | 2015-10-13 | https://docs.google.com/document/d/1VBldOimOoJ8lSw3xHFk0pz6683S3msMj5DJ6TX16mX4/edit?ts=56140656
| SOCIAL MEDIA | Jared | Social Messaging |  | 2 | 2015-10-19 | Locked and loaded.
| FRONT END | Jesse | Typeface (replacing font with Averta) |  | 1 | 2015-09-28
| FRONT END | Jesse | Design Changes (per page) | See other table | 1 | 2015-10-15 | #NAME?
Project management system
| FRONT END | Jesse | Product demo | Product demo for use at 2020 and with key influencers | 2 | 2015-10-19 | Accounts are ready to go. Tim does have a couple of changes that Jeff/BatOps are working on. | Mrkt | Segment LucidChart (just a few users) Typeform TryMyUI FullStory Indicative Tableau
| WEBSITE | JJ | Marketing Site | In progress with multiple arms | 1 | 2015-10-15
| WEBSITE | JJ | Testimonials | subsection of marketing site | 1 | 2015-10-06
| SOCIAL MEDIA | JJ | Youtube | basic name change issues for account | 2 | 2015-10-20
| SOCIAL MEDIA | JJ | Pinterest | basic name change issues for account | 2 | 2015-10-20
| CONTRACTS | Logan & Danielle | Marketo | in progress. some will be on day of rebrand | 2 | 2015-10-20
| CONTRACTS | JJ | Segment | not a lot to change | 2 | 2015-10-20 | Mostly done.
| BACK END | JJ & Logan | Google Analytics, filters and views | basic name change issues for account | 2 | 2015-10-20 | Straight forward change. Doc in note for ref.
| SOCIAL MEDIA | Joel | Affiliate partner notification |  | 2 | 2015-10-20 | Email set to go out on 10/20/2015
| COLLATERAL | Joel | Impact Radius (Ads) | Talk to Rep to Prep | 2 | 2015-10-20 | Ads and IOs are complete and will be switched over on 10/20/2015
| CONTRACTS | Joel | Emails from Partners | In coordination with Matt; need a week lead time; Talk to Rep to Prep | 1 | 2015-10-06
| CONTRACTS | Joel | Affiliate landing pages (offers) | Our Affiliates page; Impact Radius is the only other one (swap logo and language) | 2 | 2015-10-19 | IR Affiliate page will be updated with new logo and language on 10/20/2015
| CONTRACTS | Joel | Impact RAdius | duplicate
| ACCOUNTS | Joel | Lencred | Swap name (text) in scripts | 2 | 2015-10-13 | Email set to go out on 10/20/2015
| BACK END | Johnny | Schemas | Falls under database which is being handled by Dave. Mostly need to make sure we aren't going to break anything. | 1 | 2015-10-01 | Nothing needs to be done
| BACK END | Johnny | Tableau | may be minor | 1 | 2015-10-01 | Nothing needs to be done
| FRONT END | Krissie | Mobile App |  | 1 | 2015-10-07 | iOS is submitted. Android is ready to submit.
| COLLATERAL | Hang | Employee and Company Voice Mail |  | 2 | 2015-10-20 | Hang for non Member services
| SOCIAL MEDIA | Matt | Partner notifications | notify partners of change | 2 | 2015-10-20 | Release looking good for oct 20. Affiliate and partner and pre launch messages on track.
| FRONT END | Matt | CS Messaging (Phone team) | Just need to change voice mail; prompt already done | 2 | 2015-10-20 | Recordings are ready. Just need to be switched over in real time on the conversion day.
| WEBSITE | Matt | Chat System | Change name in chat account | 2 | 2015-10-20
| COLLATERAL | Matt | Telephone Scripts | Close to done | 2 | 2015-10-20
Other
| ACCOUNTS | Matt | inContact | duplicate
| CONTRACTS | Matt | Communication with Partners | In coordination with Joel; need a week lead time; partner communication email from marketing |  | dup
| COLLATERAL | NA | Office Paint Scheme
| COLLATERAL | NA | Mousepads
| COLLATERAL | NA | Values (Branded)
| COLLATERAL | NA | Terrance
| COLLATERAL | NA | Inventory stickers (asset tagging)
| ACCOUNTS | Caton | Recurly | Recipts need to be updated to new Nav | 2 | 2015-10-20 | Ready, except for email
| WEBSITE | SeanX | FB Ads | many many many ads | 2 | 2015-10-22 | Ads scheduled to startup again Thursday October 22nd
| WEBSITE | SeanX | banner ads | banner ads (Dede) | 2 | 2015-10-20 | done
| SOCIAL MEDIA | SeanX | Facebook Page URL | Will be issues. Not easy | 2 | 2015-10-20 | Done, changed to Facebook.com/navsmb Airfoil is merging Fundastic into Nav Facebook page
| Other | SeanX | Tagline | latest iteration is in Caton's email | 1 | 2015-10-05
| Other | SeanX | Brand Positioning Document (for all Nav) | Asap - already in development. Still crafting language. | 1 | 2015-09-28 | Draft shared with company. https://docs.google.com/document/d/1ymU-SK8fq4JqVUIyu-3O7D2lSWkqHuSeiaQEA-MguO4/edit
| SOCIAL MEDIA | SeanX | Wikipedia | N/A
| WEBSITE | SeanX/Buddha/Noel | App Store - Logos, Descriptions, Links | Mostly Done | 2 | 2015-10-20 | Confirmed by Noel
| SOCIAL MEDIA | Noel | iOS & Android Store | Mostly Done | 2 | 10/19/0105 | Android: Monday Evening (Noel); Will require Version Control update on Rails Side
| FRONT END | Seth | New "Nav" bar | Navigation bar | 1 | 2015-10-06 | Seth is working on this, but wants to do a full group conversation before implementing
| OFFER DATA | Hadley | Update Bookly Offer | Shared database issue forced this change to "day of" | 1 | 2015-10-14
| WEBSITE | JJ | Stress Test | Test traffic on new marketing site | 1 | 2015-10-16 | Failed around 125 concurrent connections. Will run again after second server deployed.
Note on I193: http://www.koozai.com/blog/search-marketing/how-to-change-website-domain-in-google-analytics-9918/